## Global - Site-Wide
Element / Component | Issue Type | Viewport | Description | Severity | Status | Proposed Solution | User Notes | CSS / Code Reference | Flow / State
FAB (palette button) | UX | Mobile | Orange palette FAB overlaps warning banners, numpad Done button, chart legends, and content at bottom-right on multiple pages | High | Resolved | Move FAB above bottom sheet when numpad open; add bottom margin to banners; or make FAB dismissable/repositionable |  | AdminDesigner.tsx | Multiple pages, numpad open
Monthly data tables | UX | Mobile | All monthly balance tables (Accounts, Investments, Net Worth, Debt) show only account names — dollar columns completely off-screen. No visual scroll indicator. | Critical | Resolved | Add scroll shadow/gradient on right edge of table; add "swipe →" hint; ensure -webkit-overflow-scrolling: touch |  | DataTable.tsx, *Page.tsx | Table view on mobile
Monthly data tables | Visual | Tablet | Delta and last-month columns sometimes clip at right edge when sidebar is open | Medium | Resolved | Add overflow-x-auto wrapper with min-width on table element |  | DataTable.tsx | Table view on tablet
Page title inline edit | Enhancement | Global | No visual affordance that titles are clickable/editable. Users won't discover feature. | Low | Resolved | Add subtle pencil icon on hover, or dotted underline hint |  | PageHeader.tsx | Any page, hover on title
Alert/warning banners | Visual | Desktop | Banner text occasionally clips at right edge on narrow content areas | Low | Resolved | Ensure text-wrap and max-width: 100% on banner container |  | Layout.tsx | Dashboard with warnings
Sidebar at 768px | UX | Tablet | Sidebar takes ~30% of viewport at exact 768px breakpoint. Content very cramped for data-heavy pages. | Medium | Resolved | Raise md breakpoint to 1024px, or auto-collapse sidebar at 768-1023px range |  | Sidebar.tsx | Tablet portrait/landscape
Resolved
Resolved
Resolved
Resolved
Resolved
Resolved
Resolved
Resolved

## Dashboard
Element / Component | Issue Type | Viewport | Description | Severity | Status | Proposed Solution | User Notes | CSS / Code Reference | Flow / State
Paycheck Distribution pie | Visual | Desktop | Pie chart spans full page width. User wants it at half-width with another element beside it. | Medium | Resolved | Add chart width controls to Edit Layout (half/full toggle per section) |  | DashboardPage.tsx comp-pie | Dashboard view
All chart sections | Enhancement | Desktop | No way to resize chart widths or set side-by-side. User wants pie narrow, line charts full. | High | Resolved | Add width selector (Full/Half/Third) in Edit Layout mode per chart card. Use CSS grid cols. |  | DashboardPage.tsx | Edit Layout mode
Edit Layout panel | Enhancement | Global | Only has show/hide toggles. No width, order, or size controls per chart. | High | Resolved | Add: width dropdown per section, drag-to-reorder, chart height slider |  | DashboardPage.tsx | Edit Layout mode
KPI cards in edit mode | Visual | Desktop | Cards break to single column when Edit Layout panel is open | Low | Resolved | Keep 4-col grid; move edit panel to sidebar or modal overlay |  | DashboardPage.tsx | Edit Layout mode
Net Worth donut | Visual | Desktop | Small donut in 1/3 width column of 3-col grid. Could be larger. | Low | Resolved | Consider wider donut column or size option in Edit Layout |  | DashboardPage.tsx net-worth-chart | Dashboard view
Charts | Visual | Mobile | All charts render and scale. No major issues. | Low | Resolved | No action needed — informational |  |  | Mobile dashboard scroll
Resolved
Resolved
Resolved
Resolved
Resolved
Resolved
Resolved
Resolved

## Add Snapshot
Element / Component | Issue Type | Viewport | Description | Severity | Status | Proposed Solution | User Notes | CSS / Code Reference | Flow / State
NumberInput popup | UX | Desktop | Popup overlaps form fields below it when opened | Low | Resolved | Add z-50; consider positioning above trigger if near bottom of viewport |  | NumberInput.tsx | Click any number input
NumberInput ± button | Visual | Global | ± button has same styling as number keys — not visually distinct | Low | Resolved | Add muted/different background color to ± key |  | NumberInput.tsx | Numpad open
NumberInput keyboard | UX | Desktop | No native text input fallback. Can't select/paste. Must use custom numpad. | Medium | Resolved | Add text input mode toggle on desktop; or make display field editable |  | NumberInput.tsx | Numpad open, desktop
NumberInput Done vs FAB | UX | Mobile | FAB overlaps the Done button when numpad bottom sheet is open | High | Resolved | Hide FAB when numpad is open, or raise Done button above FAB |  | NumberInput.tsx, AdminDesigner.tsx | Mobile, numpad open
Prev values distance | Visual | Desktop | Previous values shown far right of label — hard to connect label ↔ value on wide screens | Low | Resolved | Add max-width to field row; or move prev closer to input |  | EntryPage.tsx FieldRow | Desktop entry view
Submit button reachability | UX | Mobile | Full-width submit at bottom. Long scroll past many accounts to reach. | Low | Resolved | Consider sticky submit button at bottom of viewport |  | EntryPage.tsx | Mobile, many accounts
Manage Accounts auto-open | UX | Global | AccountManager now auto-expands when category has zero accounts ✅ Fixed | Low | Fixed | Auto-expand form when filtered.length === 0 |  | AccountManager.tsx | Empty category on any page
Resolved
Resolved
Resolved
Resolved
Resolved
Resolved
Resolved
Resolved

## Cash Accounts
Element / Component | Issue Type | Viewport | Description | Severity | Status | Proposed Solution | User Notes | CSS / Code Reference | Flow / State
Monthly table | UX | Mobile | Only account names visible. All dollar columns hidden off-screen. | Critical | Resolved | See Global fix #2 — scroll indicator |  | AccountsPage.tsx | Mobile view
Total row | Visual | Mobile | Total label shows but dollar amount off-screen | Medium | Resolved | Show total as summary card above table on mobile |  | AccountsPage.tsx | Mobile view
Donut chart | Visual | Mobile | Renders well, legend wraps. FAB overlaps last legend item. | Low | Resolved | Add bottom padding to chart container |  | AccountsPage.tsx | Mobile, scroll to charts
Monthly table | Visual | Desktop | Full table visible with all months and delta column ✅ | Low | Resolved | No action needed |  |  | Desktop view
Resolved
Resolved
Resolved
Resolved
Resolved
Resolved
Resolved
Resolved

## Investments
Element / Component | Issue Type | Viewport | Description | Severity | Status | Proposed Solution | User Notes | CSS / Code Reference | Flow / State
Monthly table | UX | Mobile | Account names visible but all balance columns off-screen | Critical | Resolved | See Global fix #2 |  | InvestmentsPage.tsx | Mobile view
Concentration warning | Visual | Mobile | Warning banner wraps nicely ✅ | Low | Resolved | No action needed |  |  | Mobile view
Summary KPI cards | Visual | Mobile | 2-column grid works ✅ | Low | Resolved | No action needed |  |  | Mobile view
Resolved
Resolved
Resolved
Resolved
Resolved
Resolved
Resolved
Resolved

## Debt
Element / Component | Issue Type | Viewport | Description | Severity | Status | Proposed Solution | User Notes | CSS / Code Reference | Flow / State
Monthly Balance History | UX | Mobile | Only JAN 26 column visible, rest off-screen | Critical | Resolved | See Global fix #2 |  | DebtPage.tsx | Mobile view
Credit Card Status | Visual | Mobile | Summary stats layout well ✅ | Low | Resolved | No action needed |  |  | Mobile view
Utilization bars | Visual | Mobile | Progress bars render correctly ✅ | Low | Resolved | No action needed |  |  | Mobile card details
Resolved
Resolved
Resolved
Resolved
Resolved
Resolved
Resolved
Resolved

## Net Worth
Element / Component | Issue Type | Viewport | Description | Severity | Status | Proposed Solution | User Notes | CSS / Code Reference | Flow / State
All Accounts table | UX | Mobile | Only Account + Type columns visible. Monthly balances hidden. | Critical | Resolved | See Global fix #2 |  | NetWorthPage.tsx | Mobile view
Section headers | Visual | Mobile | Color-coded CASH/INVESTMENT/DEBT separators look good ✅ | Low | Resolved | No action needed |  |  | Mobile view
All Accounts table | Visual | Tablet | Delta column clips at right edge | Medium | Resolved | Ensure overflow-x-auto and min-width |  | NetWorthPage.tsx | Tablet view
Resolved
Resolved
Resolved
Resolved
Resolved
Resolved
Resolved
Resolved

## Income
Element / Component | Issue Type | Viewport | Description | Severity | Status | Proposed Solution | User Notes | CSS / Code Reference | Flow / State
Tax % display — 100x inflated | Bug | Global | FED Withholding shows 611.0% instead of 6.11%. FED Social Security 283.9% instead of 2.84%. ALL deduction percentages multiplied by extra 100x. | Critical | Resolved | Fix: deduction % display calculates (amount / grossSemiMonthly) then formatPercent does *100. The NumberInput isPercent also does *100. Double multiplication. Remove one. |  | IncomePage.tsx ~lines 530-585, NumberInput isPercent logic | Income > Taxes & Deductions
Allocation % — 100x inflated | Bug | Global | WF Savings shows 1250.0% instead of 12.5%. 401k shows 784.6% instead of 7.85%. Same root cause as tax %. | Critical | Resolved | Allocations stored as decimals (0.125). Display uses formatPercent(*100) AND template also *100. Remove one layer. |  | IncomePage.tsx allocations section | Income > Paycheck Breakdown
NET PAY column | Visual | Mobile | Column clipped — only "$" visible for Monthly+ rows. 4th column pushed off-screen. | High | Resolved | Add overflow-x-auto to pay table; or hide NET PAY on mobile, show as sub-row |  | IncomePage.tsx pay table | Mobile view
NET PAY column | Visual | Tablet | Partially visible, clips on larger values | Medium | Resolved | Same fix as mobile — overflow-x-auto |  | IncomePage.tsx | Tablet view
Comp inputs | Visual | Tablet | All visible and readable now ✅ | Low | Resolved | No action needed — previously clipped, now resolved |  |  | Tablet view
Deductions section | UX | Mobile | Very long scroll to reach. No section navigation. | Low | Resolved | Consider section jump links or collapsible sections |  | IncomePage.tsx | Mobile, deep scroll
Resolved
Resolved
Resolved
Resolved
Resolved
Resolved
Resolved
Resolved

## Budget
Element / Component | Issue Type | Viewport | Description | Severity | Status | Proposed Solution | User Notes | CSS / Code Reference | Flow / State
Budget item names | Visual | Mobile | Severely truncated: "Ren", "Spe", "Con", "iClo", "GSu", "Fig", "Ado". Completely unreadable. | Critical | Resolved | Stack on mobile: name full-width row 1, category + amount row 2. Or card-per-item layout. |  | BudgetPage.tsx budget table | Mobile, Fixed/Variable sections
Budget item names | Visual | Tablet | Truncated: "Spectrum Int", "ConEd Electr", "Renter's Insu". Readable but not ideal. | Medium | Resolved | Widen name column; reduce category column width; responsive breakpoints |  | BudgetPage.tsx | Tablet view
KPI Emergency Fund | Visual | Tablet | 4th KPI card clips at right edge. Dollar amount partially cut off. | Medium | Resolved | Stack to 2x2 grid on tablet, or add overflow-x-auto to KPI row |  | BudgetPage.tsx KPI section | Tablet view
Delete button | Visual | Mobile | Delete (🗑) button pushed completely off-screen for all items | Medium | Resolved | Include in stacked mobile layout; or swipe-to-delete gesture |  | BudgetPage.tsx | Mobile, any budget item
Variable section | Visual | Mobile | "iClo", "GSu", "Fig" — worse than Fixed because subscription names are longer | Critical | Resolved | Same stacked layout fix as Fixed section |  | BudgetPage.tsx | Mobile, Variable section
Emergency Fund Progress | Visual | Mobile | Progress bar and % render well ✅ | Low | Resolved | No action needed |  |  | Mobile view
Savings rate warning | Visual | Mobile | Warning banner wraps correctly ✅ | Low | Resolved | No action needed |  |  | Mobile view
Resolved
Resolved
Resolved
Resolved
Resolved
Resolved
Resolved
Resolved

## Goals
Element / Component | Issue Type | Viewport | Description | Severity | Status | Proposed Solution | User Notes | CSS / Code Reference | Flow / State
Trophy stat cards | Visual | Mobile | 3-col grid works but "Major Milestones" text wraps — uneven card heights | Low | Resolved | Consider 2-col grid or min-height on cards |  | GoalsPage.tsx | Mobile view
Color hex input | UX | Mobile | Small input, hard to use on touch | Low | Resolved | Add preset color swatches as quick-pick buttons |  | GoalsPage.tsx | Mobile, achievement form
Achievement form | Visual | Mobile | Fields stack vertically, works well ✅ | Low | Resolved | No action needed |  |  | Mobile, form section
Timeline cards | Visual | Mobile | Render cleanly with tier badges ✅ | Low | Resolved | No action needed |  |  | Mobile, timeline section
Resolved
Resolved
Resolved
Resolved
Resolved
Resolved
Resolved
Resolved

## Tools
Element / Component | Issue Type | Viewport | Description | Severity | Status | Proposed Solution | User Notes | CSS / Code Reference | Flow / State
Calculator forms | Visual | Mobile | Full-width inputs, clean layout ✅ | Low | Resolved | No action needed |  |  | Mobile view
Calculator forms | Visual | Desktop | 3-column layout for Debt Fighter fields ✅ | Low | Resolved | No action needed |  |  | Desktop view
Results visibility | UX | Mobile | Results appear below form after Calculate — user may not notice without scrolling | Low | Resolved | Auto-scroll to results after calculation |  | ToolsPage.tsx | After clicking Calculate
Resolved
Resolved
Resolved
Resolved
Resolved
Resolved
Resolved
Resolved

## Settings
Element / Component | Issue Type | Viewport | Description | Severity | Status | Proposed Solution | User Notes | CSS / Code Reference | Flow / State
Page Titles section | UX | Global | Redundant now that inline editing exists. Could confuse users. | Low | Resolved | Add note: "Also editable by clicking titles on each page" or remove section |  | SettingsPage.tsx | Settings page
Designer Mode controls | Enhancement | Global | Missing: type ramp editor (h1-h6 sizes), spacing system, chart sizing controls, component-specific widths | High | Resolved | Add: Typography section (heading/body sizes, line-height), Spacing (margins, gaps), Charts (height, max-width per type) |  | AdminDesigner.tsx | Designer Mode panel
Custom CSS editor | Visual | Mobile | Editor textarea renders but very hard to use on small screen | Low | Resolved | Collapse by default on mobile; or link to external editor |  | SettingsPage.tsx, ThemeEditor | Mobile settings
Account Colors grid | Visual | Mobile | 2-column grid works ✅ | Low | Resolved | No action needed |  |  | Mobile settings
Theme presets | Visual | Mobile | Buttons wrap and are tappable ✅ | Low | Resolved | No action needed |  |  | Mobile settings
Export/Import | Visual | Mobile | Buttons accessible ✅ | Low | Resolved | No action needed |  |  | Mobile settings
Reset Data | UX | Mobile | Category reset + nuke works. Type DELETE confirmation functional. | Low | Resolved | No action needed |  |  | Mobile settings
Resolved
Resolved
Resolved
Resolved
Resolved
Resolved
Resolved
Resolved

## Sidebar & Nav
Element / Component | Issue Type | Viewport | Description | Severity | Status | Proposed Solution | User Notes | CSS / Code Reference | Flow / State
Dashboard cog menu | UX | Mobile | Always visible on mobile ✅ Actions menu works. | Low | Resolved | No action needed |  | DashboardSwitcher.tsx | Mobile sidebar
Sidebar at 768px | UX | Tablet | Takes ~30% viewport. Data pages (budget, income, accounts) very cramped. | Medium | Resolved | Raise md breakpoint or add collapsible toggle |  | Sidebar.tsx | Tablet portrait
Resize handle | UX | Desktop | Drag resize + double-click reset both work ✅ | Low | Fixed | Working as intended |  | Sidebar.tsx | Desktop sidebar edge
Mobile hamburger | UX | Mobile | Opens/closes correctly. Overlay dismisses on tap. ✅ | Low | Resolved | No action needed |  | Sidebar.tsx | Mobile header
Nav active state | Visual | Global | Active page highlighted with accent + right border ✅ | Low | Resolved | No action needed |  |  | Any page
Dashboard switcher | Visual | Tablet | Text may truncate on long dashboard names at narrow sidebar | Low | Resolved | Wider popover already implemented |  | DashboardSwitcher.tsx | Tablet, switcher open
Duplicate dashboard | UX | Global | Duplicates data + metadata correctly, switches to copy ✅ | Low | Fixed | Working as intended |  | store.ts, DashboardSwitcher.tsx | Cog menu > Duplicate
Resolved
Resolved
Resolved
Resolved
Resolved
Resolved
Resolved
Resolved

## Beta v0.1 Features
Feature | Category | Status | Notes
Glass design system | Visual | Shipped | Frosted cards, mouse glow, GlassCard
5 CSS background themes | Visual | Shipped | Midnight Pro, Neon Split, Solar Flare, Northern Glow, Electric Violet
Background image editor | Visual | Shipped | 12 presets, upload, crop, focal point, scrim
10 color themes | Visual | Shipped | 5 original + 5 grey-with-hue
Pastel + vivid chart palettes | Visual | Shipped | COLORS (fills) + VIVID (strokes)
Mouse glow effect | Visual | Shipped | CSS pseudo-element + JS tracking
Cloud sync (8 categories) | Infrastructure | Shipped | Dashboards, settings, themes, backgrounds, tool drafts
Tier system (free/pro/premium) | Infrastructure | Shipped | UpgradeGate, FeatureBadge, beta mode
Transaction Tracker | Pro Feature | Shipped | Full CRUD, search, filter, category breakdown
Paycheck X-Ray (full) | Feature | Shipped | 6 charts, waterfall, pay period table, LTI
Snapshot FAB | UX | Shipped | Camera button on all pages
Undo/redo | Feature | Shipped | Ctrl+Z, 30-state history, auto-hide after 5s
PWA manifest + icons | Infrastructure | Shipped | manifest.json, SVG icons, meta tags
Error boundary | Reliability | Shipped | Catches crashes, shows recovery UI
Pay frequency support | Data | Shipped | Weekly/biweekly/semimonthly/monthly
Share button | Feature | Shipped | Read-only links via Supabase
Month-over-month deltas | Data | Shipped | Latest this month vs latest last month
Mobile month picker | UX | Shipped | Accounts, Investments, Debt pages
NumberInput portal | UX | Shipped | createPortal escapes overflow:hidden
Scroll-to-top | UX | Shipped | On every route navigation
Editable page titles | UX | Shipped | Click any title to rename
Security audit | Quality | Clean | Zero vulnerabilities found
Accessibility audit | Quality | Shipped | aria-labels, focus-visible, heading hierarchy
Stripe integration | Infrastructure | Backlog | Need publishable key + price IDs
Charts month comparison | Feature | Backlog | Side-by-side month overlay
Notifications/reminders | Feature | Backlog | Days since last snapshot banner

## Scope Comparison
Metric | Count
Planned phases | 9
Delivered phases | 9
Unplanned features built | 38
Total features shipped | 47+
New files created | 15
Files modified | 30+
Git commits this session | 45+
Pages in the app | 14
Color themes | 10
Background themes | 17 (5 CSS + 12 photo)
Security vulnerabilities | 0
Console errors | 0